## Progress Planning and Tracking
Project Name: | SP-01 Red
Report Date: | 2022-09-20
[5 empty] | Project Plan (Sept 24) |  |  |  | Milestone #1 (Oct 22) |  |  |  | Milestone #2 (Nov 8) |  |  |  | C-Day (Dec 1)
Deliverable | Tasks | Complete% | Current Status Memo | Assigned To | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02
Robot Documentation | Setup a GitHub pages site to share robot doc. | 100% |  | Andrew | 2022-09-02: 6; 2022-09-09: 6; 2022-09-16: 6
and Certification | Document how to properly handle/ work with the robots | 95% | Working (need to add pictures) | Andrew, Jack | 2022-09-02: 10; 2022-09-09: 8; 2022-09-16: 4
| Train other teams on how to properly handle the robots (Certification) | 100% |  | Jack | 2022-09-09: 8; 2022-09-16: 4
(Research/Planning) |  |  |  |  | 2022-09-02: 8; 2022-09-09: 8; 2022-09-16: 8; 2022-09-23: 8
API Documentation | Setup GitHub pages for team to keep track of all project documentation | 0% | Working | Andrew | 2022-09-23: 4; 2022-09-30: 4
| Setup Raspberry Pi with ROS2 | 100% |  | Jack | 2022-09-23: 6; 2022-09-30: 8; 2022-10-07: 4
| Document motor ranges and IDs | 15% |  | Jack, Derek | 2022-09-23: 6; 2022-09-30: 8; 2022-10-07: 6
| Porting UXA-90 code (robot code) to ROS2 | 15% |  | Jack | 2022-10-07: 6; 2022-10-14: 4
| Design REST API Server | 0% | Working | Derek | 2022-09-16: 8; 2022-09-23: 8; 2022-09-30: 8
| Develop working API Prototype | 0% | Working | Derek | 2022-10-07: 8; 2022-10-14: 8
| Add API documentation to GitHub pages | 0% |  | Sarah | 2022-10-07: 6; 2022-10-14: 6
(Project Design) | Test API Prototype | 0% | TBD | Derek | 2022-10-14: 5; 2022-10-21: 5; 2022-10-28: 5
API Source Code | Review API Prototype design | 0% |  | Derek | 2022-10-21: 4
and Robot Source Code | Build REST API Server | 0% |  | Derek | 2022-10-21: 8; 2022-10-28: 12; 2022-11-04: 12; 2022-11-11: 12
| Write source code for API Client | 0% |  | Derek | 2022-11-04: 8; 2022-11-11: 8; 2022-11-18: 8
| Write source code for Robot Client | 0% |  | Jack, Andrew | 2022-10-21: 8; 2022-10-28: 12; 2022-11-04: 12; 2022-11-11: 12; 2022-11-18: 8
| Update GitHub Pages with all documentation | 0% |  | Sarah, Andrew | 2022-11-11: 4; 2022-11-18: 4
| Report draft | 0% |  | Sarah | 2022-11-11: 8; 2022-11-18: 6
| Test and debug all source code | 0% |  | Jack | 2022-11-11: 4; 2022-11-18: 3
(Development) | PHASE 2: Develop app to control robot | 0% |  | TBD | bar: 2022-11-04 to 2022-11-18
Final report | Presentation preparation | 0% |  | All | 2022-11-18: 3; 2022-11-25: 4; 2022-12-02: 4
| Work on final report | 0% |  | Sarah | 2022-11-18: 6; 2022-11-25: 6; 2022-12-02: 6
| Poster preparation | 0% |  | All | 2022-12-02: 8
| Final report submission to D2L and project owner | 0% |  | Jack | bar: 2022-12-02
|  |  | Total work hours | 397 | 24 | 30 | 30 | 32 | 28 | 30 | 23 | 25 | 29 | 32 | 48 | 38 | 10 | 18
* formally define how you will develop this project including source code management
Legend
Planned
Delayed
Number | Work: man hours